## Sheet1
Feature | Implementation | Complexity | Time Requirement | Cost | Members | Notes | Explanation |  | Complexity | Time Requirement | Cost
Controls | [7 empty] | 1 | We already know | Little to no time requied | Little to no cost
| Game Controller | 2 | 2 | 2 |  | Disconnected component |  | 2 | We have good knowledge, some new learning required | Minimal amount of time | Minimal cost
| VR Controllers | 4 | 3 | 3 |  | Disconnected component |  | 3 | We have broad knowlege, further learning required | Large chunk of time | Notable cost
| touchbar | 2 | 2 | 1 |  | Need to look into |  | 4 | We know little, more time needed for learning | Majority of project length | Category limit
| Headset Buttons/scroll wheel | 1 | 1 | 2 |  | Less cost, less complex (Think about L/R hand) | less positibility to exploit the testing programs and will require less precision than a touchbar; would be difficult to misclick with this | 5 | University professionals assistance required | Full allotment of time used | External funding
| Custom Handheld | 3 | 4 | 4 |  | Disconnected component |  | 6 | Industry professionals required | More time than we have | Prohibitive
| Keyboard | 1 | 2 | 1 |  | Potential easy keylogging by users, only good option for essay qs, future iteration
| Eye tracking | 5 | 5 | 5 |  | Expensive, not commonly accepted (privacy)
| drawing tablet |  |  |  |  | Future iteration
| Calculator app built in |  |  |  |  | Future iteration
| Hand tracking | 5 | 5 | 5 |  | Future iteration
Display | [5 empty] | safety consideration, zoom in ability
| VR (Existing Product) | 2 | 2 | 4 |  | RS: Let's go with VR - with a placeholder for AR. Thoughts?
| AR (Existing Product) | 3 | 3 | 5 |  | For flexibility, we could have more use cases met (i.e. using a calculator, doing outlines or taking notes) with an AR functionaility or a lens
| Monitor | 1 | 2 | 1 |  | How do we allow for user adjustment (to zoom in and better focus the lenses based on user's preference / need
| LCDs, OLED, LCoS | 3 | 3 | 2 |  | potentially lower resolution | displays to prism/mirror for redirecting light into eyes
| Waveguides | 5 | 4 | 5 |  |  | special cuts in lense to redirect light
| Wearable Displays | 3 | 2 | 3 |  | not a lot of choice on market | Prebuilt display
| Cut blue light |  |  | 1 |  | avoid eye strain
Sensors
| Camera(s) looking externally | 2 | 3 | 2 |  | Future iteration/stretch goal, roams where eyes roam | This just live streams and/or records the data and dosen't process it
| Camera watching eyes |  |  |  |  | Future iteration? | Fish eye lens
| Camera (with AI) | 5 | 5 | 2 |  | Future iteration? | Future implementation
| Infared | 3 | 3 | 3 |  | Future iteration?
| Sonar/Lidar | 3 | 3 | 2 |  | Future iteration? | Sound, light
| Microphone | 2 | 3 | 3 |  | Future iteration? | This just live streams and/or records the data and dosen't process it
| gyroscope? | 3 | 4 | 4 |  | Future iteration? | Do we care whether the test taker is moving around?
Data Security
| Two Key encryption | 5 | 5 | 1 |  |  | Industry grade encryption. Used commonly for bank details and online shopping. Requires industry grade advanced math.
| Placeholder-encryption | 1 | 1 | 3 |  | RS: let's do this - with STRONG placeholder ; ) | Doesn't actually encrypt data it's just an open slot for better encryption from external service
| Pre-implemented libraries | 2 | 2 | 1 |  | Discussed with cybersecurity prof re connectivity and he mentioned there are some libararies to implement and said Wifi would be find
Data Transfer |  | Complexity | Time Requirement | Cost
| Cellular | 4 | 4 | 3 |  | Future iteration | would need a phone plan for each device through a major carrier once done OR could do a cellular base station
| Bluetooth | 2 | 2 | 1
| WIFI | 3 | 3 | 1 |  | RS QUERY: Could we do wifi + cellular? Would that give us the best coverage / connectivity? Will do it Wifi for now with a placeholder for add + cellelur at a later date
Power
| Battery | 2 | 1 | 2 |  | RS QUERY: is there a comfort / weight factor we should take into account here? Should we leave a placeholder to do both?
| Power Supply + small battery backup | 1 | 1 | 1 |  | Will use external power supply with a small back up to save info if power is disrupted; larger battery will be a future iteration
Headset Housing
| 3D printing / customized | 3 | 3 | 3 |  | RS QUERY: does use of an existing headset also limit us to an existing display?
| Existing headset | 3 | 1 | 5 |  | RS: Which is more fun?! ; ) I like 3D printing one but I'm open....
Needs to be tamper proof and tamper evident
| more even weight distribution |  |  |  |  | Future iteration
File
| Custom file system |  |  |  |  | future iteration
standard file
additional future iteration notes
accomodate special needs (vision)
custom cell transmitter
weight redistribution